## Component 1
Annex 2 Implementation Timetable
Component 1: Strengthen the VMGD platform to provide quality climate data and information for CIS | [27 empty] | Second Extention
ACTIVITY | SUB-ACTIVITY | DELIVERABLE | LEAD | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Output 1.1 - Strengthening climate information services through improved data and interfaces | bar: 2018 Q1 to 2023 Q4
Activity 1.1.1 Improving the currency, functionality and visualization of climate data records for Vanuatu | Sub-activity 1.1.1.1 Update tropical cyclone and high-quality climate data for online Pacific Climate Change portals and VMGD centralised data management system (CliDE) | Deliverables 1.1.1.1 (a) Data updates to CliDE and to Pacific Climate Change Data Portal (b) Updated Tropical Cyclone data portal to include new homogenized data | BOM | 2020 Q2: a & b
| Train and develop high-quality climate datasets through best practice WMO quality assurance and homogenization processes |  | BOM | bar: 2019 Q3 to 2019 Q4; 2020 Q3
| Sub-activity 1.1.1.2 Digitize historic climate records, enter into CliDE and quality assurance | Deliverables 1.1.1.2 (a) Data quality control and homogization with the development of high-quality datasets completed (b) Digitized and homogenized data records for Vanuatu | BOM / VMGD | 2020 Q1: a & b; 2021 Q1: a & b; 2021 Q4: a & b; 2022 Q3: a& b; 2024 Q3: Digitise the historic data from NIWA (20 years) for the water sector
| Sub-activity 1.1.1.3 Updated standardized WMO Climate Extreme Indices for incorporation into CIS knowledge products and relevant portals | Deliverables 1.1.1.3 (a) Updated Pacific CC data portal & updated tropical cyclone data will be compiled and quality controlled with newly digitised data | BOM | bar: 2020 Q4
Activity 1.1.2 Building and strengthening user interfaces to support CIS Decision-making | Sub-activity 1.1.2.1 Upgrade VMGD IT platform including computing hardware and software | Deliverables 1.1.2.1 (a) Needs assessment for ICT equipment and infrastructure (b) Operational ICT system to support DSS tools and processes (c) CLWS Apps / web platforms developed (d) Backup systems installed | VMGD | 2019 Q3: a; 2020 Q3: b; 2020 Q4: c & d; 2021 Q4: b, c & d; 2022 Q2: c & d; 2023 Q1: c & d
| Sub-activity 1.1.2.2 Technical support for VMGD in developing CLEWS-based software application development and ground-truthing CLEWS and outreach to Next/End-Users | Deliverables 1.1.2.2 (a) Software applications modified and operational (b) CLEWS operational | BOM | bar: 2019 Q3 to 2020 Q4; 2021 Q4; 2022 Q3 to 2022 Q4
| Sub-activity 1.1.2.3 Vanuatu Climate Futures portal for delivery of climate change projections | Deliverables 1.1.2.3 a) Beta version VCFP IT platform (Version 1) established; (b) Annual update (V1.2) version of PCF portal developed and commissioned ; (c) Annual update (V1.3) version of PCF portal developed and commissioned (d) Results of user testing and feedback integrated to beta version VCFP (version 1.1 - 1.3) content and functionality | CSIRO | 2020 Q1: a; 2021 Q2: b, d; 2021 Q4: b, d; 2022 Q2: c, d; 2022 Q4: c, d
Output 1.2. Research, modelling and prediction to support CIS tools and uptake | bar: 2018 Q1 to 2023 Q4
Activity 1.2.1. Upgrading and expanding the Vanuatu observational networks | Sub-activity 1.2.1.1 Enhancing stream monitoring capabilities in the Sarakata River catchment | Deliverables 1.2.1.1 (a) River monitoring gauge procured and installed (b) Data analysed and uploaded into the CLEWS and used in monitoring reporting | VMGD | bar: 2020 Q4; 2021 Q4; 2022 Q3 to 2024 Q4
| Sub-activity 1.2.1.2 Ocean monitoring for CLEWS enhancement and inundation modelling | Deliverables 1.2.1.2 (a) Procurement and installation of wave buouys (b) Data analysed and uploaded into the CLEWS and used in monitoring reporting | VMGD | 2020 Q4: a; 2021 Q4: b; 2022 Q4: b; 2023 Q4: b; 2025 Q1: Will include the ongoing O&M checks and ensuring that the installed instruments are functioning as required.
| Sub-activity 1.2.1.3 Expanding Vanuatu's rainfall monitoring system | Deliverables 1.2.1.3 (a) Procurement and installation of AWS and ARG (b) Data analysed and used to verify downscaled weather and climate forecast information for agricultural use and in agro-models for decision support | VMGD | bar: 2020 Q4; 2021 Q4; 2022 Q3 to 2024 Q4
| Sub-activity 1.2.1.4 Expanding Vanuatu's early warning system capability | Deliverables 1.2.1.4 (a) Procurement and installation of radar weather system (b) Data analysed and used by VMGD to inform Sectors | VMGD | bar: 2021 Q4 to 2022 Q4; 2023 Q2 to 2025 Q1
Activity 1.2.2. Improved utility and function of seasonal climate forecasts | Sub-activity 1.2.2.1 Develop new seasonal impact forecasts for priority sectors | Deliverables 1.2.2.1 (a) Methodology and SOPs established; (b) Updated station datasets and data collected from ACCESS-S; (c) Downscaled end user products | BOM | 2020 Q3: a; 2020 Q4: b; 2021 Q1: c
| Sub-activity 1.2.2.2 New downscaled datasets developed and interfaced with sector-defined CIS | Deliverables 1.2.2.2 (a) Sector-needs for new impact seasonal forecast collected/available; (b) Downscaling initial results available; (c) Standard Operating Procedures (SOPs) prepared for VMGD | BOM | 2019 Q3: a; 2020 Q3: b; 2020 Q4: c
Activity 1.2.3. Long-term projections for key climate variables and climate extremes for Vanuatu | Sub-activity 1.2.3.1 Developing multi-model projections for key climate variables in Vanuatu | Deliverables 1.2.3.1 (a) V1.0 Modelling framework and downscaled CIS database established and reported; (b) V2.0 Modelling framework reviewed and updated; (c) V2.0 downscaled CIS database updated and reported; (d) V2.0 Projections data, scenarios, assessments and storylines, including final reporting | CSIRO | 2020 Q1: a; 2020 Q4: b; 2021 Q4: c, d; 2022 Q2: c, d
| Sub-activity 1.2.3.2 Downscaled projections ground-truthed and outreach to target Next/End-Users | Deliverables 1.2.3.2 .(a) V1.0 Preliminary CIS applications identified via consultations (report or similar) and sectoral training needs identified; (b) V1.0 Ground-truthed downscaled data with sectors to inform CIS products; (c) V2.0 Preliminary CIS applications identified via consultations (report or similar) and sectoral training needs identified; (d) V2.0 Ground-truthed downscaled data with sectors to inform CIS products (e) Facilitate/undertake training and related capacity development with sectors/other endusers | CSIRO | 2020 Q1: a, b; 2020 Q4: a, b; 2021 Q2: c, d, e; 2021 Q4: c, d, e; 2022 Q2: c, d, e; 2022 Q4: c, d, e
| Sub-activity 1.2.3.3 Apply Global Climate Model projections to observed datasets and undertake quality control | Deliverables 1.2.3.3 (a) Climate variables identified, initial assessment of GCMs undertaken and Version 1.0 application-ready data sets reported; (b) V1.0 Application-ready data to inform CIS products including both progress and final versions; (c) V2.0 Application-ready data reported and delivered to inform CIS products including both progress and final versions | CSIRO | 2020 Q4: a; 2021 Q2: a; 2021 Q4: a, b; 2022 Q2: c; 2022 Q4: c
| Sub-activity 1.2.3.4 Synthesise and report application-ready data in context of risk assessments for sectors, outreach to Next/End-Users | Deliverables 1.2.3.4 (a) Preliminary CIS applications identified via consultations (report or similar) and sector training needs identified; (b) V1.0 Application-ready data to inform CIS products including both progress and final versions; (c) V2.0 Application-ready data to inform CIS products including both progress and final versions; (d) Facilitate/undertake training and associated capacity development with sectors and other tyarget end-users;(e) provide content for populating Van KIRAP portal with relevant climate data layers | CSIRO | 2019 Q3: a; 2020 Q1: a; 2020 Q4: a; 2021 Q1: a; 2021 Q2: a, b, d; 2021 Q4: b, d, e; 2022 Q2: c, d; 2022 Q4: c, d, e
Activity 1.2.4. Risk-based coastal and other climate hazard analysis and mapping | Sub-activity 1.2.4.1 Mapping climate hazard hotspot exposure | Deliverables 1.2.4.1 (a) Prelimnary extreme sea level projection methods and datasets developed (progress and final technical reports); (b) Application-ready data to inform CIS products including both progress and final versions; (c) Provision of training materials and training support for sectoral end-users. | CSIRO | 2019 Q3: a; 2020 Q1: a; 2020 Q4: a; 2021 Q2: a; 2021 Q4: a; 2022 Q2: a, b, c; 2022 Q4: a, b, c
| Sub-activity 1.2.4.2 Developing projected extreme sea level probabilities for designated coastal 'hotspots' | Deliverables 1.2.4.2 (a) Coastal hazard hotspot study-sites identified, modelling framework established, preliminary CIS data and information products identifed and reported; (b) Preliminary CIS applications identified via consultations (report or similar) and sectoral training needs identified; (c) Mapped coastal innundation (and possibly erosion) risk modelling datasets and technical reports; (d) Application-ready data for sectoral case study applications (progress and final) (e) Facilitate/undertake training and related capacity development with sectors/other endusers; (f) Final reporting including all methods, technjical specifrications, data/metadata, guidance materials and associated CIS products | CSIRO | 2019 Q3: a; 2020 Q1: a; 2020 Q4: a; 2021 Q2: a; 2021 Q4: a, b; 2022 Q2: b, c, e; 2022 Q4: c, d, e, f
Activity 1.2.5. Vulnerability mapping of the coastal zone in Vanuatu | Sub-activity 1.2.5.1 Develop biogeochemical and hydrodynamic model for coastal areas of Vanuatu | Deliverables 1.2.5.1 (a) Modelling framework developed, hazrads identified and preliminary CIS data and information products identifed and reported; (b) Model configured and run for climate change scenarios, hazards and CIS data outputs (including progress technical reports; (c) Training and Outreach activities on modelling current and future changes and what this means for key sectors in coastal areas of Vanuatu; (d) Final reporting including all methods, technical specifications, data/metadata, guidance materials and associated CIS products | CSIRO | 2020 Q1: a; 2020 Q4: a, b; 2021 Q2: a, b; 2021 Q4: a, b, c; 2022 Q2: a, b, c; 2022 Q4: a, b, c, d
| Sub-activity 1.2.5.2 Develop ocean acidification and marine impact projection maps. | Deliverables 1.2.5.2 (a) Preliminary CIS applications identified and sectoral training needs identified; (b) V1.0 Ocean impact projection datasets and CIS products developed, communicated/applied and uploded to portal (including progress and final technical reports; (c) V2.0 Ocean impact projection datasets and CIS products developed, communicated/applied and uploded to portal (including progress reports); (d) Training and Outreach activities on current and future potential impacts and what this means for key sectors in coastal areas of Vanuatu; (e) Final reporting including all methods, technjical specifications, data/metadata, guidance materials and associated CIS products | CSIRO | 2020 Q1: a; 2020 Q4: a, b, d; 2021 Q2: a, b, d; 2021 Q4: a, b, d; 2022 Q2: a, b, c, d; 2022 Q4: c, d, e
Activity 1.2.6. Developing tailored Agro-met predictions for target cropping systems | Sub-activity 1.2.6.1 Develop Agro-met information portal including new on-line IT infrastructure and software (VaCSA prototype) | Deliverables 1.2.6.1 (a) VaCSA prototype installed (b) Improved VaCSA developed and integrated with CCD | APCC | bar: 2019 Q3 to 2019 Q4; 2020 Q4; 2022 Q3 to 2023 Q2
| Sub-activity 1.2.6.2 Collecting, modeling, analysis and reporting of agro-met data to determine optimal agriculture crop planning options | Deliverables 1.2.6.2 (a) Agriculture sector baseline assessment report; (b) SOPs developed and conduct training program; (c) Agro-Met data analysis report; (d) Agro-Met data analysis report | APCC | 2020 Q2: b; 2020 Q4: a; 2021 Q4: b; 2023 Q1: c, d
| Sub-activity 1.2.6.3 Undertaking field trials and validation prior to incorporation into DSS delivery platforms, ground-truthing and outreach with target Next/End-Users | Deliverables 1.2.6.3 (a) Training Programs Conducted; (b) Field trial SOPs; (c) Field trial report | APCC | 2021 Q3: a; 2021 Q4: a; 2022 Q1: a; 2022 Q3: b, d; 2023 Q2: a, c, e
| Sub-activity 1.2.6.4 Develop the crop-climate diary customised for agro-met data collection | Deliverables 1.2.6.4 (a) CCD developed and training program conducted (b) Improved CCD developed and integrated with VaCSA | APCC | bar: 2019 Q1 to 2020 Q1; 2022 Q3 to 2023 Q2

## Component 2
Annex 2 Implementation Timetable
Component 2: Demonstrating the value of CIS at the sectoral and community levels | [27 empty] | Second Extention
ACTIVITY | SUB-ACTIVITY | DELIVERABLE | LEAD | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Output 2.1 - CIS implemented within target sectors
Activity 2.1.1. Investigating the climate sensitivity, potential impacts and vulnerability of food crops in Vanuatu to secure future food security | Sub-activity 2.1.1 Establishment of demonstration plots for food crops in order to show the use of CIS at the community level | Deliverables 2.1.1 (a) Dmonstration sites established (b) demonstrated climate resilient crops and agricultural practices | Agriculture | 2020 Q4: a; 2021 Q4: a & b; 2022 Q4: b; 2023 Q4: b; 2024 Q3: Funding available (balance) to futher expand to other sites - this will be for 2024 only
| Sub-activity 2.1.2 Conduct threshold analysis of crops using climate models | Deliverables 2.1.2 (a) Climate change projections for agricultural sector (Activity 1.2.3) (b) Products and information on climate projections for the sector | Agriculture | 2020 Q3: a; 2020 Q4: b; 2021 Q3: a; 2021 Q4: b; 2022 Q2: a; 2022 Q3: b; 2022 Q4: a & b; 2023 Q1: a & b; 2023 Q2: a& b
| Sub-activity 2.1.3 Develop CIS tools, products and information for the target sector | Deliverables 2.1.3 (a) CIS tools, products and information developed and disseminated | Agriculture | bar: 2020 Q4 to 2021 Q2; 2022 Q1; 2022 Q4 to 2023 Q2; 2024 Q1 to 2025 Q4
Activity 2.1.2 Improving food security in Vanuatu by using climate information to prepare for and respond to temperature impacts on coastal fisheries | Sub-activity 2.1.2.1 Establish management plans for MPAs | Deliverables 2.1.2.1 (a) Management plans developed and implemented (b) Climate change projections for fisheries sector (Activity 1.2.3) | Fisheries | 2020 Q3: a; 2020 Q4: b; 2021 Q3: a & b; 2022 Q2: b; 2022 Q4: b; 2023 Q3: b; 2024 Q2: Intergration of Buoy data into the Management Plans
| Sub-activity 2.1.2.2 Building knowledge to respond to extreme climate events | Deliverables 2.1.2.2 (a) Community monitoring programme established (b) Surveys undertaken of marine habitats (c) Annual reports | Fisheries | 2020 Q3: a & b; 2020 Q4: c; 2021 Q3: a & b; 2021 Q4: c; 2022 Q4: c; 2023 Q3: c
| Sub-activity 2.1.2.3 Develop alternative food preservation methods | Deliverables 2.1.2.3 (a) Storage facilities renovated (b) Trainings on fish preservation methods | Fisheries | 2021 Q3: a,b; 2022 Q3: b; 2023 Q2: b
| Sub-activity 2.1.2.4 Community engagement and awareness | Deliverables 2.1.2.4 (a) Talored CIS products and information (b) Community awareness campaigns and events | Fisheries | 2020 Q4: a; 2021 Q4: a,b; 2022 Q2: a; 2022 Q4: b; 2023 Q3: b
Activity 2.1.3 Upgrade the standard infrastructure design in the Vanuatu Public Works Department using climate data on low–lying ‘hotspot’ and coastal erosion areas | Sub-activity 2.1.3.1 Develop climate data for 'hotspots' | Deliverables 2.1.3.1 (a) Database of bathymetric and topographic data (b) Coastal inundation maps for flood–prone (‘hotspots’) | Infrastructure | 2020 Q4: a; 2021 Q4: b; 2022 Q2: a & b; 2023 Q1: a& b; 2023 Q3: a & b
| Sub-activity 2.1.3.2 Update design standards for infrastructure e.g. road structures, bridges, culverts and seawalls | Deliverables 2.1.3.2 (a) Design standards updated (b) Provincial Civil Engineers trained in using coastal flooding and inundation data and design standard to design climate resilient structures | Infrastructure | bar: 2023 Q1 to 2023 Q3
| Sub-activity 2.1.3.3 Training and capacity building of Public Works Department personnel | Deliverables 2.1.3.3 (a) Public Works Department staff trained in LIDAR collection method and CIS for future infrastructure and design civil structure | Infrastructure | bar: 2020 Q2 to 2021 Q2; 2022 Q1; 2023 Q1 to 2025 Q4
Activity 2.1.4 Increasing climate resilience in flood prone areas - Sarakata Flood Plain | Sub-Activity 2.1.4.1 Develop and implement a Flood Management and Response Plan for the Sarakata catchment | Deliverables 2.1.4.1 (a) Flood management and Response Plan (b) Flood early warning system (c) Water Resource Management Committee established | Water | 2020 Q4: a; 2021 Q2: b & c; 2022 Q1: b & c; 2023 Q1: b & c
| Sub-activity 2.1.4.2 Undertake groundwater modelling to support Urban Water Management | Deliverables 2.1.4.2 (a) Groundwater model (b) Findings incorporated into Urban Water Management plans | Water | bar: 2020 Q2 to 2021 Q2; 2021 Q4; 2022 Q4 to 2023 Q3
| Sub-activity 2.1.4.3 Develop and enhance CIS products and information for the community | Deliverables 2.1.4.3 (a) Tailored CIS products and information for sector (b) Community awareness campaigns and events | Water | bar: 2020 Q3 to 2021 Q2; 2022 Q3; 2023 Q1 to 2023 Q3; 2024 Q1 to 2025 Q4
Activity 2.1.5 Minimizing the impacts of climate variability and change on tourism development through supporting adaptation | Sub-activity 2.1.5.1 Develop and implement Standard Operating Procedures (SOP) and Standard Guidelines for tourism operators | Deliverables 2.1.5.1 (a) Standard Operating Procedures and Guidelines (b) Awareness campaigns for local tourism bungalow design | Tourism | bar: 2020 Q2 to 2021 Q2; 2022 Q1; 2023 Q1 to 2023 Q4
| Sub-activity 2.1.5.2 Identification of future investment opportunities at national and provincial level | Deliverables 2.1.5.2 (a) Climate projections for the sector (Activity 1.2.3) (b) Impact and risk assessments for local tourism sites (c) Report and maps on future tourist zones or 'hotspots' based on climate projections | Tourism | 2020 Q4: a; 2021 Q1: b; 2021 Q4: a; 2022 Q1: b; 2022 Q3: c; 2023 Q1: c; 2024 Q2: Use of drone to get additional data
| Sub-activity 2.1.5.3 Informing tourism operators of climate change projections and impacts at the local level | Deliverables 2.1.5.3 (a) Tailored CIS products and information for sector (b) Community awareness campaigns and events | Tourism | 2021 Q2: a; 2021 Q3: b; 2022 Q2: b; 2023 Q1: a & b
Output 2.2 - CIS is incorporated into community practices | bar: 2018 Q1 to 2023 Q4
Activity 2.2.1 Establishing community CIS sites | Sub-activity 2.2.1.1 Undertake detailed assessment of proposed Climate Centres | Deliverables 2.2.1.1 (a) Assessments of Climate Centres (b) Report and recommendations | VMGD | 2019 Q3: a; 2019 Q4: a & b
| Sub-activity 2.2.1.2 Establishment of Climate Centres | Deliverables 2.2.1.2 (a) Six Climate Centres established including refurbishment, information resourcing, community activities etc | VMGD | 2021 Q1: a (1 centre); 2021 Q3: a (1 centres); 2022 Q1: a (2 centres); 2022 Q3: a (2 centres)
|  | (b) Assessment of Climate Centres and recommendations for continued roll-out of additional Centres | VMGD | bar: 2022 Q2; 2024 Q1 to 2025 Q4
|  | (c) Six Climate Centres established including refurbishment, information fitting etc in remaining six sites or Annual Climate Information field days undertaken at remaining Centre sites* | VMGD | 2022 Q2: c; 2022 Q3: c; 2022 Q4: c; 2024 Q4: Expansion of the awareness to other 6 sites (note this is not establishing CCC) and assess impact of the CCC in the first 6 sites
| Sub-activity 2.2.1.3 Establishment of community climate champions | Deliverables 2.2.1.3 (a) Development of criteria for selection of community champions (b) Terms of reference developed for Community champions (c) Champions selected (d) Reports from the Centres / Champions | VMGD | 2020 Q1: a & b; 2020 Q2: c; 2020 Q4: d; 2021 Q4: d; 2022 Q4: d; 2023 Q4: d
| Sub-activity 2.2.1.4 CIS demonstration activities and events | Deliverables 2.2.1.4 (refer Activity 3.1.1. & 3.3.1) (a) CIS knowledge tools, information and products produced and disseminated (b) Outreach activities and campaigns | VMGD | 2020 Q4: a & b; 2021 Q4: a & b; 2022 Q4: a & b; 2023 Q4: a & b; 2024 Q3: Development of CIS tools based on the Survey results
Output 2.3 - A socio-economic benefit analysis for Vanuatu using the customised Pacific CIS cost-benefit Framework is produced | bar: 2018 Q1 to 2023 Q4
Activity 2.3.1. Undertake a socio-economic benefit analysis for Vanuatu using the customized Pacific CIS Cost-benefit Framework | Sub-activity 2.3.1 Develop and populate SEB database | Deliverable 2.3.1 (a) V1.0 SEB framework and database established and preliminarily populated (GTAP file/CSV files); (b) V2.0 SEB framework and database updated and populated (from V1.0); plus relevant communication collateral (fact sheet, brochure etc); (c) V3.0 SEB framework and database updated and populated (from V2.0); plus relevant communication collateral (fact sheet, brochure etc); (d) Guidance materials around use of SEB analysis | CSIRO | 2020 Q1: a; 2020 Q4: b; 2021 Q2: b; 2021 Q4: b; 2022 Q2: c, d; 2022 Q4: c, d
| Sub-activity 2.3.2 Compile annual SEB reports | Deliverable 2.3.2 (a) V1.0 Annual CIS SEB Report; (b) V2.0 Annual CIS SEB Report; (c) V3.0 Annual CIS SEB Report; (d) Communication collateral including sectoral report cards and dashboard design/content for VK Portal and SEB metrics to inform project M&E | CSIRO | 2020 Q1: a; 2020 Q4: a, b; 2021 Q2: a, b; 2021 Q4: a, b; 2022 Q2: c, d; 2022 Q4: c, d
Notes:
1. * The Climate Centres will be initially implemented in six communities at the Provincial level and assessed. The assessment and lessons learned from the establishment of these Centres will guide decisions as to viability of continued roll-out of Centres in more remote locations, or whether alternatives would be more viable e.g. annual climate field days at communities. This activity i.e. establishment of CC will also be dependent upon a final decision based on the MTR recommendation and may shift to a greater emphasis on utilising networks in the outer regions rather than the establishment of CC's as per the Provincial level

## Component 3
Annex 2 Implementation Timetable
Component 3: Development of CIS tools and engaging with stakeholders through outreach and communications | [27 empty] | Second Extention
ACTIVITY | SUB-ACTIVITY | DELIVERABLE | LEAD | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Output 3.1 - Traditional knowledge is incorporated into climate information services in Vanuatu
Activity 3.1.1 Integrating Traditional Knowledge into CIS tools and information | Develop and implement a project-wide traditional knowledge plan | Deliverables (a) TK strategy; (b) Expanded TK data observational network; (c) Annual reports | VMGD | 2020 Q1: a; 2020 Q4: b & c; 2021 Q4: c; 2022 Q4: c; 2023 Q4: c
| Support to the sectors to incorporate traditional knowledge with scientific data into application in the case study sites | (a) CIS products produced for target sectors | VMGD | bar: 2020 Q3 to 2020 Q4; 2021 Q4; 2022 Q4; 2023 Q4
| Design CIS information products combining traditional knowledge with scientific data for communities | (a) CIS products for community stakeholders | VMGD | bar: 2020 Q3 to 2020 Q4; 2021 Q4; 2022 Q4; 2023 Q4
Output 3.2 - Development of CIS tools and information products
Activity 3.2.1. Developing CIS tools and information products for target end-users | Sub-activity 3.2.1.1 Customising CIS decision support systems (DSS) for target sectors and communities | Deliverables (a) Decision support tools developed and disseminated | VMGD | bar: 2020 Q3 to 2020 Q4; 2021 Q4; 2022 Q4; 2023 Q4
| Sub-activity 3.2.1.2 Suite of forecast-based CIS ground-truthed, operationalised and outreached with Next/End-Users | Deliverables 3.2.1.2 (a) Impact based seasonal forecasts operationased (b) Seasonal climate forecase products ground-truthed, validated and launched | BOM | bar: 2020 Q3 to 2022 Q4
Output 3.3 - Implementing knowledge management, engagement and outreach across sectors and communities
Activity 3.3.1 Knowledge management, communication and outreach | Sub-activity 3.3.3.1 Develop the knowledge management, communication and outreach strategy | Deliverables 3.3.1 (a) Knowledge management, communication and outreach strategy developed | SPREP | bar: 2021 Q4 to 2022 Q1
| Sub-activity 3.3.3.2 Develop and disseminate CIS knowledge tools, information and products to stakeholders | Deliverables 3.3.2 (a) Public access repository(s) established for CIS knowledge products, information (b) Knowledge tools, information and products produced and disseminated (c) Outreach activities and campaigns | SPREP | 2020 Q3: a; 2020 Q4: b & c; 2021 Q4: b & c; 2022 Q4: b & c; 2023 Q4: b & c

## Component 4
Annex 2 Implementation Timetable
Component 4. Strengthening the institutional capacity for long-term implementation of CIS in decision-making | [27 empty] | Second Extention
ACTIVITY | SUB-ACTIVITY | DELIVERABLE | LEAD | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
|  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Output 4.1 - Institutional capacity to implement CIS across sectors strengthened | bar: 2018 Q1 to 2023 Q4
Activity 4.1.1. Strengthening CIS coordination and response mechanisms for target sectors | Sub-activity 4.1.1.1 Review existing Vanuatu Government policy, planning and associated institutional / governance arrangements | Deliverable 4.1.1.1. (a) Sector policy review and sectoral governance reports (b) Decision support tree for CIS dissemination to sectors and uptake within sectors | VMGD | bar: 2018 Q1 to 2020 Q4
| Sub-activity 4.1.1.2 Develop 5 sector CIS Action and Communications Plans | Deliverable 4.1.1.2 (a) Sector Action and Communication Plans for five sectors (b) Annual reports on workplan activities and impact | VMGD | bar: 2018 Q1 to 2019 Q1
Activity 4.1.2 Building institutional and project capacity in Monitoring and Evaluation, Environmental and Social Safeguards and Gender | Sub-activity 4.1.2.1 Develop and implement the Project Gender & Social Inclusion Plan | Deliverables 4.1.2.1 (a) Review of the current Gender Action Plan with recommendations (b) Gender & Social Inclusion Strategy and Action Plan finalised (c) Report on actions and strategies implemented across project activities | SPREP | 2020 Q2: a; 2021 Q4: b; 2022 Q2: c; 2022 Q4: c; 2023 Q2: c; 2023 Q4: c; 2025 Q1: The reporting and the M&E for the duration 2024 will clearly present the impacts and how the project has featured against the ESMP
| Sub-activity 4.1.2.2 Develop and implement the Environmental and Social Safeguards Management Plan | Deliverables 4.1.2.2 (a) ESS assessment and ESM Plan (b) Updated Plan based on Sector case studies (c) Report on actions implemented across project activities | SPREP | 2019 Q2: a; 2021 Q4: b; 2022 Q2: c; 2022 Q4: c; 2023 Q2: c; 2023 Q4: c
| Sub-activity 4.1.2.3 Develop and implement the M&E Plan | Deliverables 4.1.2.3 (a) M&E Plan (b) M&E report on progress against M&E framework | SPREP | bar: 2020 Q1 to 2024 Q4; 2025 Q3 to 2025 Q4
Output 4.2 - Training of personnel leads to strengthening of institutional capacity | bar: 2018 Q1 to 2023 Q4
Activity 4.2.1 Training packages building knowledge and skills in meteorology and climate tools | Sub-activity 4.2.1.1 Develop training package for sector coordinators and practitioners | Deliverables 4.2.1.1 (a) Training needs analysis and report (b) Training packages (c) Training delivered and annual reports on training submitted | VMGD | 2019 Q4: a; 2020 Q3: b; 2020 Q4: c; 2021 Q4: c; 2022 Q4: c; 2023 Q4: c
Activity 4.2.2 Establishing a mentoring programme to strengthen capacity and knowledge | Sub-activity 4.2.2.2 Develop mentoring programme for VMGD | Deliverables 4.2.2.2 (a) Mentoring programme developed with clear objectives, outcomes and implementation plan | VMGD | bar: 2021 Q4; 2024 Q1 to 2025 Q4
| Sub-activity 4.2.2.2 Implementation of mentoring programme actions | Deliverables 4.2.2.2 (a) Secondments and placements undertaken (b) Annual attachments (internships, cadetships) in VMGD and five target sectors (c) Participant reports submitted | VMGD | 2022 Q2: a & d; 2022 Q3: a & d; 2022 Q4: c; 2023 Q2: a & d; 2023 Q4: c

## C-Band Radar
Milestones | 2022 |  | 2023 | [11 empty] | 2024 | [11 empty] | 2025
| Jan | Feb | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
EOI Report (from EEs)
Pending Information from EEs
Implementing Agency timelines if all outstanding issues are addressed | bar: 2022 Jan to 2022 Feb
Submit updates on meeting the GCF conditions | bar: 2023 Feb
SPREP internal process to approve Call for full proposal | bar: 2023 Mar
Call for full proposals | bar: 2023 Mar to 2023 May
Tender opening, Evaluation and Reporting | bar: 2023 May
Tender negotiation | bar: 2023 May
SPREP Internal approval for contracting | bar: 2023 Jun
Contract award | bar: 2023 Jun
Commencement of Contract | bar: 2023 Jul
11 months average timeline for manufacturing to handover (includes, training at factory, installation & operations) | bar: 2023 Jul to 2024 May
Retention period (to be negotiated but usually 12 months) | bar: 2024 Jun to 2025 Mar
Final payment of Contract and closure | bar: 2025 Mar
Demonstration of Radar operations and relevance (considering 12 months of operation) | bar: 2024 May
Cyclone /wet seasons | bar: 2023 Jan to 2023 Apr; 2023 Nov to 2024 Apr; 2024 Nov to 2025 Apr
Current project completion date
Proposed second extension period for VanKIRAP